## Milestones
Milestone | Owner | Due | Status | Notes
Scope lock | Yuchen | 2025-10-25 | Planned
Environment ready | Eric | 2025-10-27 | Planned
Baseline charts | Dhanrithii | 2025-10-31 | Planned
Iteration package | Team | 2025-11-02 | Planned

## Tasks
Task | Owner | Deadline | Status | Notes
Define research questions | Yuchen | 2025-10-25 | Planned
Init repo + README | Eric | 2025-10-27 | Planned
Create baseline charts (2–4) | Dhanrithii | 2025-10-31 | Planned
Write insights memo | Yuchen | 2025-10-31 | Planned

## Risks
Risk | Mitigation
Geospatial tooling learning curve | Limit to station-level aggregates first
Data formatting inconsistencies | Create a station name mapping table
Time constraints | Narrow scope to 1–2 lines for prototype